## English
Roles and Responsibilities Chart
Role | Responsibility | Person in Charge | Deadline
Project Manager | Oversee the entire event, set timelines and deadlines, monitor the progress of each team. | Toshitaka Ueda | Until event ends
Marketing Lead | Develop and execute the promotion plan, manage social media posts, execute email marketing, and enhance audience reach. | Issei Jo | December 1, 2024
Public Relations Lead | Create and distribute press releases, handle media relations, manage event media exposure before and after the event. | Runa Nishitani | November 30, 2024
Social Media Manager | Manage Instagram, Twitter, LinkedIn accounts, create content, interact with followers, and post in real-time. | Toshitaka Ueda | Until event ends
Website Manager | Design and manage the event website, execute SEO strategies, manage the registration form, and update web pages. | Akira Tokuda | Until event ends
Partnership Manager | Coordinate with sponsors and municipalities, adjust event participants, support networking, and coordinate with related institutions. | Jun Sato | Until event ends
Event Coordinator | Manage on-site operations, arrange booths, guide visitors, handle issues, and oversee the event schedule. | Toshitaka Ueda | December 1, 2024
Technical Support Lead | Manage the online platform, operate audio-visual equipment, handle technical issues, and support Wi-Fi and digital devices at the venue. | Toshitaka Ueda | Until event ends
Design Lead | Create visual designs for the event, including posters, brochures, and social media graphics. | Toshitaka Ueda | November 25, 2024
Email Marketing Lead | Manage the email list, send event-related emails, dispatch reminder emails, and analyze email open and click rates. | Toshitaka Ueda | December 1, 2024
Sponsorship Coordinator | Negotiate with local governments and supporting organizations, coordinate with sponsors, and assist in promoting municipalities. | Sota Miyake | November 30, 2024
Media Relations Lead | Act as the point of contact for the media, arrange interviews, and strategize to maximize media exposure for the event. | Toshitaka Ueda | Until event ends
Feedback Collection Lead | Create and distribute post-event surveys, collect and analyze feedback from participants, and propose improvements for the next event. | Toshitaka Ueda | December 10, 2024